Resolution No. 12-13

A Resolution of the Board of Directors of the Sweetwater Springs Water District Adopting the 2014-2019 Capital Improvement Program

WHEREAS, the Board of Directors has reviewed the overall Capital Improvement Program and has established priorities for the upcoming six year period;

NOW THEREFORE BE IT RESOLVED, that the Board of Directors of the SWEETWATER SPRINGS WATER DISTRICT, Sonoma County, California, hereby adopts the 2014-2019 Capital Improvement Program attached as Exhibit A hereto, effective July 1, 2012.

BE IT FURTHER RESOLVED, that this Resolution supercedes and replaces Resolution 11-02.

I hereby certify that the foregoing is a full, true, and correct copy of a Resolution duly and regularly adopted and passed by the Board of Directors of the SWEETWATER SPRINGS WATER DISTRICT, Sonoma County, California, at a meeting held on July 5, 2012, by the following vote.

Director				Aye		No

Sukey Robb-Wilder

Jim Quigley

Rich Holmer

Gaylord Schaap

Victoria Wikle

Sukey Robb-Wilder

President of the Board of Directors

Attest: Julie A. Kenny

Clerk of the Board of Directors

Exhibit A

Sweetwater Springs Water District

Capital Improvement Program

2014-2019

Board of Directors

Sukey Robb-Wilder, President

Jim Quigley, Vice President

Rich Holmer, Financial Coordinator

Gaylord Schaap

Victoria Wikle

General Manager

Steve Mack

2014-2019 Sweetwater Springs Water District Capital Improvement Program

July 5, 2011

Capital improvements are an important element of the District’s work effort.  The District has an aging infrastructure, an unacceptable amount of unaccounted for water and District staff spend too much time reacting to leaks in the distribution system.  Table 1. 2014-2019 Capital Improvement Program (CIP) lists needed District projects by year and includes estimated costs.  The ranking criteria for the priority of capital projects are:

- Number of leaks.

- District time dedicated to repair the leaks.

- Costs per Customer.

- Potential Liability to the District.

- Storage and booster stations based upon system requirements for fire flow, and storage requirements.

- Impacts to the optimum operation of the system.

- Elimination of as many dead-end lines as possible, which affect both water quality and pressure.

| Table 1. Sweetwater Springs Water District Proposed 2014-2020 CIP Projects by Year; Revised Order |  |  |  |  |
| --- | --- | --- | --- | --- |
| Year | Projects | Estimated Cost | Cost per service | Comments |
| 2014 |  |  |  |  |
|  | Old Monte Rio Road (GV) – Replace 5,800 lf of existing main and appurtenances commencing at the Handy Andy Booster and proceeding westerly, 50 services. | $936,000 | $18,720 | Needed for flows, fire protection, customer water quality, leaks |
|  | 2014 Total | $936,000 |  |  |
| 2015 |  |  |  |  |
|  | Hidden Valley Rd (GV) – Replace 3,900 lf of existing main and appurtenances on Hidden Valley Rd, 67 services. | $656,000 | $9,791 | Needed for flows, fire protection, customer water quality, leaks; need to figure out project |
|  | Guernewood Lane (GV) - – Replace 1,800 lf of existing main and appurtenances and abandon 200 lf of redundant 4 – inch main along Hwy 116, 20 services. | $318,000 | $15,900 | Has been pushed down from past priority lists; needed. |
|  | 2015 Total | $974,000 |  |  |

| 3rd Year |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Canyon 1 (Rio Nido) Replace approximately 3,900 ft of existing mainline and 75 services along Canyon 1 Rd., Memory Ln., Memory Park Rd. | $890,000 | $13,284 | needed project; moving this up. |
|  | 3rd Year (2016?) Total | $890,000 |  |  |
| 4th Year |  |  |  |  |
|  | Park Ave. (GV) replace approximately 2900 lf of main line on Park Ave. and McLane, 37 services. Loop two deadend lines. | $688,000 | $18,595 | pushed down, but needed |
|  | Cherry St. (GV) replace approximately 440 lf of main line, 13 services. | $126,000 | $9,692 | do with Park Ave. |
|  | 4rd (2017?) Year Total | $814,000 |  |  |
| 5th Year |  |  |  |  |
|  | Wright Drive main pressure zone. – (GV) Replace approximately 1,120 ft of existing mainline and 18 associated services along Wright Dr. and Wright Ln. | $275,000 | $15,278 |  |
|  | Woodland Drive – mainline replacement. (GV) Replace approximately 1,900 ft of existing mainline and 27 associated services along Woodland Dr in the main pressure zone. | $400,000 | $14,815 |  |
|  | Monte Rio Treatment Plant Green Sand Filter Replacement | $130,000 | NA | Investigation/analysis needed on replacing this |
|  | 5th Year (2019?) Total | $805,000 |  |  |
|  | Priority List (5 Years) Total | $4,419,000 |  |  |
|  | Other Projects |  |  |  |
|  | Schoeneman pressure zone- main line replacement. (GV) Replace approximately 3,000 ft of existing mainline and 47 associated services along Highland Way, Sunset Ave, Woodland Dr, Laurel Way and Morningside Drive. (requires completion of Schoeneman Tank) | $744,300 | $15,836 |  |
|  | Highway 116 (MR) Replace approximately 850 ft of main line. | $280,000 |  | Do with Main Street |
|  | Main St (MR) Replace approximately 800 ft of mainline along Main St. | $180,000 |  |  |
|  | Upper Summit Tank - Construct a storage tank with a nominal capacity of approximately 120,000 gallons at the District–owned site on McLane Avenue. Project to include relocation/ construction of the existing hydro-pneumatic pump station. | $490,000 |  | Do we wait on development for these tanks? Does new development contribute? |
|  | Natoma Tank – Replace the existing 10,000 gallon storage tank with a 30,000 storage tank. 2005 cost estimate | $190,000 |  |  |
|  | Schoeneman Tank– Replace the existing 10,000 gallon tank with a 30,000 gallon storage tank. 2005 cost estimate | $127,000 |  |  |
|  | Wright Drive upper pressure zone. – (GV) Replace approximately 3,280 ft of existing mainline and 47 associated services along Wright Dr, Glenda Dr, Natoma Dr. (requires completion of Natoma Tank) | $800,000 | $17,021 |  |
|  | Other Projects Total | $2,811,300 |  |  |
|  | Total Projects Amount | $7,230,300 |  |  |